Work Breakdown Structure Template for Atlantic Supply Chain Management System

**\*Bold signifies Milestone**

**Prepared by:** **Atlantic team** **Date: 18.9.2017**

|  |  |  |
| --- | --- | --- |
| Task Name | Duration | WBS |
| **WBS\_Atlantic\_Supply\_Chain\_System** | **28+4 days** | **0** |
| **Initiating Phase** | **5 days** | **1** |
| Technical Enablement Workshop | 1 day | 1.1 |
| Business Case Examination | 1 day | 1.2 |
| Business Case Analysis | 3 days | 1.3 |
| Completed Initiating Phase | 0 days | 1.4 |
| **Planning Phase** | **20 days** | **2** |
| **Writing Documentation** | **5 days** | **2.1** |
| Project Documentation | 2 days | 2.1.1 |
| Software Documentation | 3 days | 2.1.2 |
| **Software Design** | **3 days** | **2.2** |
| Identify Functionalities | 1 day | 2.2.1 |
| Describe Solutions | 2 days | 2.2.2 |
| **Learning Programming Tools** | **12 days** | **2.3** |
| SAP Cloud Platform | 2 days | 2.3.1 |
| Spring/Spring Tools Suite | 5 days | 2.3.2 |
| Other Programming Libraries | 5 days | 2.3.3 |
| Completed Planning Phase | 0 days | 2.4 |
| **Software Development** | **3? days** | **3** |
| Software Construction | 3? days | 3.1 |
| New software solution ready | 0 days | 3.2 |
| **Project Closing** | **4 days** | **4** |
| Project Introspection | 2 days | 4.1 |
| Writing Post Project Documentation | 2 days | 4.2 |
| Completed Closing Phase | 0 days | 4.3 |
|  |  |  |